SIM Expiry Voice Bot

Scale-Up & Operations Plan

Client: Globe Telecom, Philippines     Version: v1.0 -Draft

Peak target: 10,000 calls/day     Ramp window: 14 days     Owner: OBZ Delivery

01. Calling Process How lists flow from Globe into scheduled calls each day

End-to-end flow

Each weekday follows a fixed cycle: Globe provides the subscriber list, OBZ validates and schedules it, calls run within a regulated window, and the EOD report drives the next-day decision.

| Globe CRM / Data Team Generates weekly call list in csv | → | OBZ Ingestion Validate, sort by tier | → | Scheduler Assign to days, time slots, retry logic | → | Calling Window 9:00 AM – 5:00 PM PHT | EOD Report + Gate Decision Scale up / hold / scale down |
| --- | --- | --- | --- | --- | --- | --- | --- |

Weekly list delivery

Globe's CRM / Data team delivers a weekly call list covering the upcoming Monday through Friday. This is the single source of truth for who gets the call. OBZ does not source, modify, or supplement the list independently.

| Delivery deadline | Friday 4:00 PM PHT (list for following Mon-Fri) |
| --- | --- |
| Delivery method | Email |
| Acknowledgement | OBZ confirms receipt and validation by Friday 7:00 PM PHT |
| Required fields | Customer Number, SIM_expiry_date |
| List ownership | Globe is responsible for DNC pre-filter and compliance. |
| Urgent top-up | Globe may deliver a mid-week Tier 1 surge list. |

Post the Scaleup/Hypercare period, the operations will be handed over to

2-week scheduler - day-by-day volume plan

The scheduler allocates the validated list across 14 calling days, respecting the daily cap and prioritizing Tier 1 (most urgent) subscribers first. Retry records (up to 3 attempts per subscriber) are held in a retry bucket and slotted into available capacity.

| Day | Date | Phase | Target Calls | Status |
| --- | --- | --- | --- | --- |
| 1 | D+0 | Smoke test | 100 | Manual watch |
| 2 | D+1 | Smoke test | 300 | Manual watch |
| 3 | D+2 | Controlled ramp | 750 | Auto-monitor |
| 4 | D+3 | Controlled ramp | 1,500 | Auto-monitor |
| 5 | D+4 | Controlled ramp | 2,500 | Auto-monitor |
| 6 | D+5 | Weekend diagnostic | 100 | Minimal batch |
| 7 | D+6 | Weekend diagnostic | 100 | Minimal batch |
| 8 | D+7 | Acceleration | 3,500 | Auto-monitor |
| 9 | D+8 | Acceleration | 5,000 | Auto-monitor |
| 10 | D+9 | Acceleration | 6,500 | Auto-monitor |
| 11 | D+10 | Full production | 8,000 | Auto-monitor |
| 12 | D+11 | Full production | 10,000 | Auto-monitor |
| 13 | D+12 | Full production | 10,000 | Sustain |
| 14 | D+13 | Full production | 10,000 | Sustain |

Scheduler logic -step by step

| Scheduler Step | Detail |
| --- | --- |
| 1. Receive weekly list | Globe delivers list by Friday 4:00 PM PHT covering the following Mon-Fri. Format: csv. |
| 2. Validate & filter | OBZ validates format |
| 3. Sort by tier | Tier 1 (1-3 days to expiry) → Tier 2 (4-7 days) → Tier 3 (8-14 days). Within each tier, sort by expiry date ascending (most urgent first). |
| 4. Assign to days | Distribute across calling days up to the daily cap. Tier 1 records always fill first. Any overspill moves to the next day's Tier 1 bucket. |
| 5. Schedule in the platform | Create a schedule using the platform feature. |
| 6. Retry bucket | At end of each calling day: NO_ANSWER and BUSY records (up to 3 total attempts) move to the retry bucket. |
| 7. Uncontactable flag | After 3 failed attempts, the record is flagged as UNCONTACTABLE in EOD report. Globe CRM team decides: either roll-over to next week or trigger SMS/push fallback. |
| 8. List refresh | Mid-week Globe may deliver an urgent top-up list (e.g. Tier 1 surge). |

02 Scale-Up / Scale-Down Gate Criteria How we decide each day whether to advance, hold, or pull back

Every EOD report triggers a gate decision. The OBZ Delivery Lead and Globe Product Owner jointly review the metrics and apply the table below. The decision is logged in the war room channel and carried into the next day's scheduler.

| Decision | Trigger Conditions | Volume Action | Notification |
| --- | --- | --- | --- |
| SCALE UP | All of: Answer rate >= 25% + Completion rate >= 60% + Zero P0 bugs | Advance to next volume tier per 2-week plan. | OBZ PM notifies Globe PM. Documented in war room channel. |
| HOLD | Any one metric misses by <= 20% of threshold, AND no P0 bug. | Keep same volume for one more day. Re-evaluate at next EOD. | OBZ PM flags in EOD report with root-cause note. |
| SCALE DOWN | Any of: Answer rate < 15% OR Completion rate < 40% | Reduce next-day volume by 50%. Diagnose before re-ramping. | OBZ PM + Delivery Lead notify Globe PM. Written RCA within 24 hrs. |
| PAUSE | Active P0 bug. | Stop all calls immediately. | Globe execs copied on email. |

HOLD persists for a maximum of 2 consecutive days. If the metric does not recover by Day 3, the decision automatically escalates to SCALE DOWN and a root-cause analysis is required.

03 Funnel Analysis Measuring efficiency at every stage from list to confirmed renewal

The voicebot funnel has 7 stages. Tracking all of them - not just the headline answer rate - reveals exactly where volume or quality is lost and surfaces the right lever to pull.

| Stage | Event | Formula |
| --- | --- | --- |
| 1 List | Records received from Globe | Total Customer numbers in file |
| 2 Validated | Passed format checks | Validated / Received |
| 3 Attempted | Calls placed by platform | Attempted / Validated |
| 4 Connected | Call answered by subscriber | Connected / Attempted (Answer Rate) |
| 5 Engaged | Subscriber stays on > 10 sec | Engaged / Connected |
| 6 Completed | Subscriber hears full message & responds | Completed / Engaged |
| 7 Agreed | Subscriber confirms SIM renewal | Agreed / Completed (Conv. Rate) |
| Overall conversion rate (Agreed / Dialed) |  | Agreed / Attempted |

04 Sample Call QA Structured checks to catch issues before they affect scale

Automated metrics tell you what happened. Sample call reviews tell you why. Run the following checks daily and weekly throughout the 14-day ramp.

| Check Type | Frequency / Sample Size | What to Evaluate |
| --- | --- | --- |
| Random call listen | Daily: 5-10 connected calls | ASR accuracy (did it transcribe correctly?), correct script played, appropriate pauses, correct disposition recorded. Flag any call where the wrong outcome was logged. |
| Error call review | Daily: 100% of ERROR and PARTIAL dispositions | Identify failure cause: ASR timeout, TTS failure, line drop, platform error. Group by error type. If any single error type > 5% calls, raise as P1 issue in EOD report. |
| Conversion quality check | Weekly: 10 COMPLETED calls across tiers | Did the subscriber genuinely agree or was there ambiguity in their response? Were they given time to respond? Was the SIM expiry date communicated clearly? Flag any script improvement opportunities. |
| Globe spot-check | Weekly: Globe PM listens to 5 calls | Globe product owner reviews call experience independently. Gives sign-off that the customer experience is on-brand and compliant. |

05 Optimal Calling Time Analysis Finding the best hours to maximize answer rate and conversion

Calling time is one of the highest-leverage variables in the campaign. The approach is: collect data uniformly in Week 1, then shift allocation toward proven windows in Week 2.

The key metrics to optimize will be “Completed” and “Engaged” rate.

Initial time-slot design

| Time Window | Slot | Week 1 Allocation | Week 2 Target Allocation | Hypothesis (PH market) |
| --- | --- | --- | --- | --- |
| 9:00 – 11:00 AM | Slot A | 25% of daily cap | Adjust based on data | Moderate -commuters, early risers. Lower for prepaid. |
| 11:00 AM – 1:00 PM | Slot B | 25% of daily cap | Adjust based on data | Good -subscribers checking phone during mid-morning break. |
| 1:00 – 3:00 PM | Slot C | 25% of daily cap | Adjust based on data | High -post-lunch, phone usage peaks for mobile-first users. |
| 3:00 – 5:00 PM | Slot D | 25% of daily cap | Adjust based on data | Highest expected -commute, home time. Best window for prepaid PH market. |

End-of-Day Report

Date: [DATE]     Day: [N] of 14

| Metric | Today | T-1 | Δ vs. T-1 |
| --- | --- | --- | --- |
| Calls Dialled - Target | [N] |  | — |
| Calls Dialled - Actual | [N] |  | [+/-N] |
| Calls Connected | [N] |  | [+/-N] |
| No Answer (all retries exhausted) | [N] |  | [+/-N] |
| Busy | [N] |  | [+/-N] |
| System Errors | [N] |  | [+/-N] |
| Total Call Duration (minutes) | [N] |  | [+/-N] |
| Avg. Call Duration -Connected (seconds) | [N] |  | [+/-N] |
| Connection Rate (Connected / Dialled) | [N]% |  | [+/-N] |
| Agreed to Keep SIM Active (count) | [N] |  | [+/-N] |
| Conversion Rate (Agreed / Connected) | [N]% |  | [+/-N] |
| Opt-Out Rate (Opt-outs / Connected) | [N]% |  | [+/-N] |
| Retries Queued for Tomorrow | [N] |  | — |
|  | FINOPS |  |  |
| LLM Inference Cost | USD [N] |  | [+/-N] |
| Total Daily Spend | USD [N] |  | [+/-N] |
|  | ISSUES & CHANGES |  |  |
| Open P0 issues | [N] |  | [+/-N] |
| Open P1 issues | [N] |  | [+/-N] |
| Changes deployed today | [describe or None] |  | — |
| Changes pending approval for tomorrow | [describe or None] |  | — |
|  | TOMORROW'S PLAN |  |  |
| Target call volume | [N] |  | — |
| Expected list from Globe (ETA) | [time] |  | — |
| Calling window | 9:00 AM - 7:00 PM PHT |  | — |
| Phase gate status | [Go / Hold - reason] |  | — |

Call Detail Log

Date: [DATE]  Calling window: 9:00 AM - 5:00 PM PHT

| Total Dialed [N] | Connection Rate [N]% | Agreed to Keep SIM [N] | Conversion Rate [N]% |
| --- | --- | --- | --- |

| # | Number | Status | Call Duration | Agreed to Keep SIM Active | Retry # | Timestamp (PHT) | Disposition Code |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 09171234567 | Connected | 0:42 | Yes | 1 | 09:05:12 | COMPLETED |
| 2 | 09282345678 | No Answer | — | N/A | 1 | 09:05:45 | NO_ANSWER |
| 3 | 09173456789 | Connected | 1:10 | No | 1 | 09:06:02 | PARTIAL |
| 4 | 09284567890 | No Answer | — | N/A | 2 | 14:02:30 | NO_ANSWER |
| 5 | 09175678901 | Busy | — | N/A | 1 | 09:07:14 | BUSY |
| 6 | 09286789012 | Connected | 0:55 | Yes | 1 | 09:08:00 | COMPLETED |
| 7 | 09177890123 | Rejected | — | N/A | 1 | 09:08:47 | REJECTED |
| 8 | 09178901234 | Connected | 0:38 | Yes | 3 | 17:45:01 | COMPLETED |

Field definitions:

Status: Connected | No Answer | Busy | Rejected | Voicemail | Error

Agreed: Yes = subscriber confirmed SIM renewal / No = declined / N/A = call not connected

Priority Tier: Tier 1 = SIM expires in 1-3 days (urgent) / Tier 2 = 4-7 days / Tier 3 = 8-14 days

Disposition: COMPLETED | PARTIAL | NO_ANSWER | BUSY | REJECTED | OPT_OUT | INVALID | ERROR

Retry #: Max 3 attempts per subscriber per day (attempts 1-3 in different time windows).